## Summary
Aratika — Project Tracker
Live status of what is built and what is left. Edit the Tracker tab; these totals update automatically.
Status | Count
Done
To do
Future ideas
Total items
% complete (excl. future)

## Tracker
# | Category | Item | Status | Priority | Notes
1 | Foundation | Next.js 16 + React 19 + TypeScript + Tailwind setup | Done | -
2 | Foundation | Supabase auth — login, register, callback | Done | -
3 | Foundation | Gated dashboard + auth-aware navbar | Done | -
4 | Foundation | Moved project off OneDrive to C:\dev\aratika | Done | - | Fixed file-sync / build issues
5 | Information | Homepage (election-urgency layout) | Done | -
6 | Information | Parties directory + 6 party pages | Done | -
7 | Information | MPs directory + filters | Done | -
8 | Information | All 123 MP profiles (122 enriched) | Done | - | Collins still basic (page down)
9 | Information | Interactive electorate map (official boundaries + 2023 results) | Done | -
10 | Information | Bills tracker — list + detail pages | Done | -
11 | Information | Policy Hub — 10 topics + per-topic pages | Done | - | Party positions still to source
12 | Learn | Learn hub + 6 modules x 4 tiers | Done | -
13 | Learn | Interactive widgets (seat allocator, build-gov, bill journey, two-votes, reveal cards) | Done | -
14 | Learn | Quizzes + progress (localStorage + account sync) | Done | -
15 | Learn | XP, levels & badges + progress banner | Done | -
16 | Learn | Kids section (Kiri mascot, confetti, stickers) | Done | -
17 | Premium | Premium gate (preview + upsell) | Done | -
18 | Premium | Take Action studio — 4 letter/submission templates | Done | -
19 | Premium | Stripe checkout + webhook + portal | Done | - | Live & tested
20 | Premium | subscriptions + learn_progress tables (RLS + grants) | Done | -
21 | Premium | Pricing page (/subscription) | Done | - | NZ$20 / month
22 | Premium | Manage-billing button on dashboard | Done | -
23 | Pages | Parliament overview page (/parliament) | To do | High | Broken nav link
24 | Pages | Elections results pages (/elections) | To do | High | Broken nav link
25 | Pages | News feed (/news) | To do | Medium | Broken nav link
26 | Pages | Glossary (/glossary) | To do | Medium | Footer link
27 | Pages | About / Our Sources (/about) | To do | Medium | Footer link
28 | Pages | Public Polls page (/polls) | To do | Low | Footer link
29 | Pages | Legal — Privacy, Terms, Contact | To do | High | Needed before launch
30 | Features | Search | To do | Medium
31 | Features | Compare tool | To do | Low
32 | Features | Bookmarks & alerts (dashboard) | To do | Medium | Needs table + RLS
33 | Data | Live Parliament data (votes, divisions, member-in-charge) | To do | Medium | Needs API integration
34 | Data | Policy positions per party (Policy Hub detail) | To do | Medium | Source from manifestos
35 | Data | Judith Collins profile | To do | Low | parliament.nz page down
36 | Launch | Register domain (aratika.nz / .org.nz) | To do | High
37 | Launch | Project email (hello@aratika.nz) | To do | Medium
38 | Launch | Deploy to hosting (Vercel) | To do | High
39 | Launch | Switch Stripe to live mode | To do | High | When launching
40 | Launch | GST / business registration | To do | Medium | Check with IRD / accountant
41 | Future | Te Reo Maori language layer | Future | -
42 | Future | Children's civic education expansion | Future | -
43 | Future | AI assistant (Phase 3) | Future | -
44 | Future | AI-assisted letter drafting | Future | -
45 | Future | Org / classroom subscription tier | Future | -
46 | Future | Video explainer layer | Future | - | Parked