## Summary
Aratika — Project Tracker
Live status of what is built and what is left. Edit the Tracker tab; these totals update automatically.
Status | Count
Done
To do
Future ideas
Total items
% complete (excl. future)

## Tracker
# | Category | Item | Status | Priority | Notes
1 | Foundation | Next.js 16 + React 19 + TypeScript + Tailwind setup | Done | -
2 | Foundation | Supabase auth — login, register, callback | Done | -
3 | Foundation | Gated dashboard + auth-aware navbar | Done | -
4 | Foundation | Moved project off OneDrive to C:\dev\aratika | Done | - | Fixed file-sync / build issues
5 | Information | Homepage (election-urgency layout) | Done | -
6 | Information | Parties directory + 6 party pages | Done | -
7 | Information | MPs directory + filters | Done | -
8 | Information | All 123 MP profiles (122 enriched) | Done | - | Collins still basic (page down)
9 | Information | Interactive electorate map (official boundaries + 2023 results) | Done | -
10 | Information | Bills tracker — list + detail pages | Done | -
11 | Information | Policy Hub — 10 topics + per-topic pages | Done | - | Party positions still to source
12 | Learn | Learn hub + 6 modules x 4 tiers | Done | -
13 | Learn | Interactive widgets (seat allocator, build-gov, bill journey, two-votes, reveal cards) | Done | -
14 | Learn | Quizzes + progress (localStorage + account sync) | Done | -
15 | Learn | XP, levels & badges + progress banner | Done | -
16 | Learn | Kids section (Kiri mascot, confetti, stickers) | Done | -
17 | Premium | Premium gate (preview + upsell) | Done | -
18 | Premium | Take Action studio — 4 letter/submission templates | Done | -
19 | Premium | Stripe checkout + webhook + portal | Done | - | Live & tested
20 | Premium | subscriptions + learn_progress tables (RLS + grants) | Done | -
21 | Premium | Pricing page (/subscription) | Done | - | NZ$20 / month
22 | Premium | Manage-billing button on dashboard | Done | -
23 | Pages | Parliament overview page (/parliament) | To do | High | Broken nav link
24 | Pages | Elections results pages (/elections) | To do | High | Broken nav link
25 | Pages | News feed (/news) | To do | Medium | Broken nav link
26 | Pages | Glossary (/glossary) | To do | Medium | Footer link
27 | Pages | About / Our Sources (/about) | To do | Medium | Footer link
28 | Pages | Public Polls page (/polls) | To do | Low | Footer link
29 | Pages | Legal — Privacy, Terms, Contact | To do | High | Needed before launch
30 | Features | Search | To do | Medium
31 | Features | Compare tool | To do | Low
32 | Features | Bookmarks & alerts (dashboard) | To do | Medium | Needs table + RLS
33 | Data | Live Parliament data (votes, divisions, member-in-charge) | To do | Medium | Needs API integration
34 | Data | Policy positions per party (Policy Hub detail) | To do | Medium | Source from manifestos
35 | Data | Judith Collins profile | To do | Low | parliament.nz page down
36 | Launch | Register domain (aratika.nz / .org.nz) | To do | High
37 | Launch | Project email (hello@aratika.nz) | To do | Medium
38 | Launch | Deploy to hosting (Vercel) | To do | High
39 | Launch | Switch Stripe to live mode | To do | High | When launching
40 | Launch | GST / business registration | To do | Medium | Check with IRD / accountant
41 | Future | Te Reo Maori language layer | Future | -
42 | Future | Children's civic education expansion | Future | -
43 | Future | AI assistant (Phase 3) | In progress | - | v1 built — see AI Companion rows
44 | Future | AI-assisted letter drafting | Future | -
45 | Future | Org / classroom subscription tier | Future | -
46 | Future | Video explainer layer | Future | - | Parked
47 | AI Companion | Ask Aratika companion — v1 (grounded chat, login-gated) | Built | - | Sonnet 4.6, retrieval+cited, 15/day free 100/day premium
48 | AI Companion | Run companion_usage migration (0003) in Supabase | To do | High | Required before it works
49 | AI Companion | Add ANTHROPIC_API_KEY to .env.local | To do | High | From console.anthropic.com
50 | AI Companion | Streaming responses | To do | Med | Token-by-token for snappier feel
51 | AI Companion | Conversation history persistence | To do | Med | Save chats per user
52 | AI Companion | Account-sync prefs + plan across devices | To do | Med | Survey answers + plan ticks to Supabase
53 | AI Companion | Embeddings retrieval upgrade | To do | Low | Sharper on vague/conceptual questions
54 | AI Companion | 'Explain this page' button on pages | To do | Med | Beyond the chat suggestion
55 | AI Companion | Usage monitoring + cost alerts / tune limits | To do | Med | Watch Anthropic spend
56 | AI Companion | Abuse hardening (server rate-limit, injection tests) | To do | Med | Before public launch
57 | Legislation Reader | Immersive bill reader (summary, policy breakdown, stage timeline, have-your-say, full text, highlights) | Built | - | Steps 1-4 complete; /legislation/[slug]
58 | Legislation Reader | Basic/Detailed plain-language toggle | Built | - | 1/21 basic versions done; rest pending quota
59 | Legislation Reader | Finish Basic plain-language versions (--simplify) | To do | High | 20 bills left; Gemini quota resets / Anthropic Thu
60 | Legislation Reader | Finish bill stage backfill (--stage-only) | To do | Med | 13 bills left; AI quota / Anthropic
61 | Legislation Reader | Approve remaining enriched bills in /editor | To do | Med | 15 pending review
62 | Legislation Reader | Enrich remaining current bills (~80) so all covered | To do | Med | AI quota / Anthropic
63 | Legislation Reader | Unify Bills page to immersive format; retire static snapshot (bills-data.ts) | To do | Med | DECISION PAUSED - 2 systems currently
64 | Legislation Reader | Exact-quote auto-highlighting (re-enrich for exact quotes/clause refs) | To do | Low | Current is best-effort match; Anthropic
65 | Legislation Reader | Official XML feed for exact original full-text formatting | Future | Low | Optional fidelity upgrade
66 | Legislation Reader | Lazy-render / paginate very large bills (e.g. Planning Bill ~1M chars) | To do | Low | Perf
67 | Editorial / Pipeline | Add ANTHROPIC_API_KEY (swap from free Gemini) | To do | High | Thursday; one-line, auto-switch
68 | Editorial / Pipeline | Regenerate Gemini API key (was shown in chat) | To do | Med | Hygiene
69 | Editorial / Pipeline | Daily ingest cron: add GitHub repo secrets | To do | Med | NEXT_PUBLIC_SUPABASE_URL, SUPABASE_SERVICE_ROLE_KEY, LEGISLATION_RSS_URLS
70 | Editorial / Pipeline | Editor management UI (add/remove editors without SQL) | To do | Low
71 | Editorial / Pipeline | Bulk-approve for straightforward factual items | Future | Low
72 | MP Impact | Phase 2: harvest MP activity (members bills, questions, speeches) via Parliament Open Data API | To do | Med | Portal was down; retry / PCO key
73 | MP Impact | Phase 3: voting/conscience records + neutral MP activity comparison | Future | Med | Votes not in any API yet (data req #849)
74 | Learn | New modules: How to enrol & vote, How a government is formed, Having your say, How policies work | Built | - | 4-tier; live in /learn
75 | Learn | Treaty of Waitangi & Māori representation module | To do | Med | DEFER to subject-matter expert author (founder request)
76 | Learn | Further proposed modules: central vs local govt; who runs elections / vote safety; finding trustworthy info & misinformation; understanding political ideas | Future | Low | From Learn review - 2nd batch
77 | Rollout | Phased launch system (LAUNCH_PHASE flag, nav/footer filter, route redirects, /coming-soon) | Built | - | src/constants/features.ts
78 | Rollout | Phase 1 = Election Central (current launch focus) | In progress | High | elections, battlegrounds, map, parties, MPs, policies, learn, onboarding
79 | Rollout | Deepen election theming of homepage | To do | Med | Gated parliament/news/premium; can theme hero/sections further
80 | Rollout | Phase 2 = Accountability — flip LAUNCH_PHASE=2 | Future | - | parliament, bills, legislation reader, take-action, news, dashboard, premium
81 | Rollout | Phase 3 = Engage & scale — LAUNCH_PHASE=3 | Future | - | Ask Aratika AI, polls, teacher curriculum, Te Reo, org tiers